## Guidance Summary
Ocean Community Empowerment and Nature Grants Programme (OCEAN) - GUIDANCE SUMMARY
Effective risk management ensures the consistent and proactive identification and handling of opportunities and risks within defined tolerance levels across projects, programmes, or organisations. It promotes transparency, constructive challenge, innovation, and excellence, driving the successful achievement of objectives. Developing a Risk Register will help you appraise your options, evaluate alternatives and make informed decisions, as such it will help with your logframe and theory of change (and vice versa). Whilst Defra is prepared to accept some risk associated with the challenges of working in difficult environments, testing new approaches, to achieve marine-poverty reduction outcomes, it has a low appetite for Safeguarding, Operational, Fiduciary and Reputational Risks. When Submitting your Application If you are applying for an OCEAN Partnership Grant, you will need to use this template to submit your risk register with your application. Guidance is provided in the notes worksheets of the template. At application stage, Partnership Grants are required to complete both the Project Risk Register and Delivery Chain Risk Map. Please read the notes on these two pages before completing the different sections of the template. When Implementing your Project Risk registers are live documents, regularly reviewed, updated and improved. If you are successfully awarded funding for your project, both OCEAN Community Grants and Partnership Grants will be required to actively maintain a Risk Register using this template. When maintaining the Risk Register as part of the management of your project, you will be required to actively update the Project Risk Register, Delivery Chain Risk Map and Issues Register. You will be required to submit updates using this template on a six-monthly basis in line with the core reporting process. When updating the risk register, any New / Emerging risks from the previous update that are now ongoing risks should be changed to 'open' status in the dropdown list of the relevant column. Any risks that are closed / resolved since the last update should have the status changed to closed, with the date it was closed recorded and confirmed whether the risk materialised / became an issue. The reason why the risk has been closed should be detailed in the ‘What’s changed’ column and dated. All open risks need to be updated as required, but at least every six months. In particular, the inherent or residual risk ratings should be reviewed, any mitigations should be updated and dated, and it is essential that the ‘What’s changed’ column is updated. The ‘What’s changed’ update should outline how the risk context has changed since the last review period. If it is felt that there is no update for an open risk, it should be outlined why there is no update since the last review period. Updates to the ‘What’s changed’ column for all open risks should be dated, and all previous entries should be left in the cell for a historical record with the most recent entry at the top of the cell.
Risk Register Conducting a risk assessment and developing your risk register should involve evaluating inherent and residual risks while identifying and understanding the triggers and indicators that will verify the realisation of the risk. When completing the template it is best to avoid vague or broad risks, such as general political instability or the possibility of fraud, and instead focus on specific, realistic, and immediate risks relevant to upcoming project activities. Each project should include at least one fiduciary, safeguarding, delivery chain, and Gender Equality, Disability and Social Inclusion (GEDSI) risk, with a focus on 5–10 key risks that are actively managed with practical mitigation plans. The Risk Register should remain a dynamic document, evolving as risks emerge, resolve, or change over the project’s lifecycle. Delivery Chain Risk Map (DCRM) The delivery chain risk map identifies risks specific to the delivery model and funding structure, some of which may overlap with the project risk register if they affect overall outcomes. It should include at least one overarching, high-level risk that reflects the overall risk of the chosen delivery model, whether through direct implementation or delivery partners. Please ensure to complete the Delivery Chain Risk Map (DCRM) before submitting your application and that the lead organisation and project partners identified are consistent with the project budget and application form. Issues Register An issues register is a tool used to document and track problems or challenges that arise during a project's implementation. It records details such as the nature of the issue, its impact, the actions taken to address it, and its resolution status. Unlike a risk register, which focuses on potential future risks, an issues register deals with current, real-time problems that require immediate attention and management. The issues register should be actively maintained as part of the management of your project and does not need to be completed when submitting your application.

## Guidance Risk Register
Ocean Community Empowerment and Nature Grants Programme (OCEAN) Risk Register Template - GUIDANCE
Risk Description | Date Added | Enter in the date that you added the identified risk into this register using the format: DD/MM/YYYY. The risk date does not change, it remains as a historical record of when the risk was first identified.
| Risk Name | Give your identified risk a succinct single sentence title. For example: Seasonal weather patterns impact local availability of project supplies.
| Risk Status | What is the status of the identified risk, is it: - New / Emerging means that it has not been fully realised as a present risk but is on the horizon and gaining momentum. - Open means that it is present and/or ongoing. - Closed means that it the risk materialised/didn't materialise and is no longer relevant or has been resolved. Please choose the risk status from the drop down menu in this column.
| Description of risk | Describe the risk succinctly in 1-3 sentences with a good, clear understanding of the three key elements of a risk: - the cause of the risk - the risk event or situation itself - the impact of the risk on the project
| Risk Type | Seven risk types are of interested: A contextual risk is one that is present in the space and location in which you are working. For example, risks may arise in challenging external settings such as conflict-affected areas, economically or environmentally fragile areas, or politicised settings. A delivery risk is a situation or event that will impact you or your partners' ability to deliver the programme. For example, the low resource capacity of your implementing partner(s) could prevent the programme from delivering against its stated objectives. Other delivery risks may arise around procurement disruptions or technical hurdles. This is likely to be higher for innovative or high impact projects. A Gender Equality, Disability and Social Inclusion (GEDSI) risk refers to the potential negative impact that your project or its activities may have on gender equality, which aims to remove the unequal power relations between different gender identities in the pursuit of equal rights, responsibilities, and opportunities for all, or marginalised or vulnerable groups within a society or community. A safeguarding risk is an occurrence that could pose a threat to the protection of the health, well-being and human rights of individuals, which allow people — especially children, young people and vulnerable adults — to live free from abuse, harm and neglect. Every project should record at least one safeguarding risk. An operational risk relates to internal capacity to effectively oversee implementation of the project and duty of care to staff, including professional competence, experience and appropriate level of resource in managing the project and funds. An example could be that staff are exposed or not adequately protected from infectious diseases within their work. A fiduciary risk is one that arises when funds are not used for the intended purposes; do not achieve value for money; and/or are not properly accounted for within the project. Risks such fraud or misappropriation are recorded within this category, as are exchange rate fluctuations or other financial management issues. All projects should record at least one fiduciary risk. A reputational risk is one that will pose detriment to the organisation's reputation or public image due to certain activities, associations, or perceptions. Please choose the relevant risk category from the drop down menu in this column.
| Risk Owner | Who is the owner of the risk? Who is responsible for monitoring and taking action on this identified risk? The person could be within your organisation or within your downstream implementing partner organisation. There can only be one risk owner per risk. Enter their full name, their job title and specify which organisation they are from.
Inherent Risk | Probability | The Inherent Risk is the rating of the risk that exists as it stands or naturally occurs, prior to any mitigating actions being put in place. Rare (<5%) - May occur only in exceptional circumstances Unlikely (>5%<20%) - Could occur at some time Possible (>20%<50%) - Might occur at some time Likely (>50%<80%) - Will probably occur in most circumstances Almost certain (>80%) - Is expected to occur in most circumstances Please choose the probability risk rating from the drop down menu in this column.
| Impact | Inherent Risk is the rating of the risk that exists as it stands or naturally occurs, prior to any mitigating actions being put in place. Insignificant - Easily handled with almost no impact on project outcomes / objectives Minor - Causes some rework or reassessment in limited areas, with limited impact on project outcomes / objectives Moderate - Causes additional work and reassessment but impact on project outcomes / objectives is containable Major - Causes significant rework, modification or reassessment of project to avoid one or more project outcomes / objectives being unmet Severe - Causes failure of project to meet outcomes / objectives, or closure of project Please choose the impact risk rating from the drop down menu in this column.
| Risk Rating | Inherent Risk is the rating of the risk that exists as it stands or naturally occurs, prior to any mitigating actions being put in place. It is determined by the Probability and Impact rating, and will be automatically calculated to be one of the following: Minor - Limited reduction in outcomes if this occurs Moderate - Higher but still limited loss in outcomes if this occurs Major - Outcomes reduced if this occurs but some important outcomes still likely Severe - Very significant reduction in outcomes when this occurs
Risk Mitigation | Risk Response Type | Responses to risk can be categorised in to one of the following. Types of risks that may negatively affect (threats) the project’s ability achieve its outcomes: Avoid - Make the uncertain event certain Reduce - Change the impact and/or probability of the threat Transfer - Ownership maintained but part of the risk transferred to a third party Share - Multiple parties share the risk on a pain/gain share basis Accept - Threat accepted, including the full impacts if the risk materialises, but do not take any further action Prepare contingent plans - Threat accepted for now but with a contingent plan if the situation changes Types of risks that may positively affect (opportunities) the project’s ability achieve its outcomes: Exploit - Make the uncertain event certain by taking appropriate action Enhance - Change the impact and/or probability of the opportunity Transfer - Ownership is maintained but part of the risk is transferred to a third party Share - Multiple parties share the risk on a pain/gain share basis Accept - Accept that the opportunity might be realised but do not take any further action Please choose the action from the drop down menu in this column.
| Mitigating Action | Detail the actions that the risk owner(s) will take to mitigate against the risk and if there are any controls that can be put in place or exercised to manage the risk. Example entry: Implement robust safeguarding measures by providing training for staff and community members on ethical practices, establishing clear reporting mechanisms for misconduct, and ensuring regular audits to protect vulnerable groups during the delivery of marine conservation initiatives. Staff will be required to complete training on an annual basis and procedures will be reviewed regularly to ensure they are appropriate and effective.
Residual Risk | Probability | The Residual Risk is the rating of the risk if all mitigation actions are successfully and effectively implemented. You can expect the residual risk to be lower than the inherent risk due to the actions taken the mitigate against the event occurrence or impact. Rare (<5%) - May occur only in exceptional circumstances Unlikely (>5%<20%) - Could occur at some time Possible (>20%<50%) - Might occur at some time Likely (>50%<80%) - Will probably occur in most circumstances Almost certain (>80%) - Is expected to occur in most circumstances Please choose the probability risk rating from the drop down menu in this column.
| Impact | The Residual Risk is the rating of the risk if all mitigation actions are successfully and effectively implemented. You can expect the residual risk to be lower than the inherent risk due to the actions taken the mitigate against the event occurrence or impact. Insignificant - Easily handled with almost no impact on project outcomes / objectives Minor - Causes some rework or reassessment in limited areas, with limited impact on project outcomes / objectives Moderate - Causes additional work and reassessment but impact on project outcomes / objectives is containable Major - Causes significant rework, modification or reassessment of project to avoid one or more project outcomes / objectives being unmet Severe - Causes failure of project to meet outcomes / objectives, or closure of project Please choose the impact risk rating from the drop down menu in this column.
| Risk Rating | The Residual Risk is the rating of the risk if all mitigation actions are successfully and effectively implemented. You can expect the residual risk to be lower than the inherent risk due to the actions taken the mitigate against the event occurrence or impact. It is determined by the Probability and Impact rating, and will be automatically calculated to be one of the following: Minor - Limited reduction in outcomes if this occurs Moderate - Higher but still limited loss in outcomes if this occurs Major - Outcomes reduced if this occurs but some important outcomes still likely Severe - Very significant reduction in outcomes when this occurs Please choose the overall risk rating from the drop down menu in this column.
Updates | What's changed this quarter | Risks should be regularly reviewed (at least every quarter), and updates should form a brief summary of what has changed since the risk was entered originally. Have any event(s) occurred that led to the risk increasing, decreasing or remaining steady in rating? How has the wider risk context changed in the meantime? Have new mitigations been undertaken since the last update? If the risk is being closed, what led to it being resolved? This 'What's changed' column does not need to be filled in when you add in a new risk to the register. The new entry should be dated, and all previous entries should be left in the cell for a historical record with the most recent entry at the top of the cell. Example entry: 21/01/2024: Seasonal weather patterns continue to impact on the local availability of supplies needed for the project and we are running out of our stock. However, a supplier in the neighbouring country has now been identified and contacted to determine if an order can be placed and shipped across the border. 17/01/2024: Seasonal weather patterns have begun. This is impacting on the local availability of project supplies, which may start having an impact on project delivery. We are starting to explore alternative sources. 14/01/2024: Seasonal weather patterns are expected. We are aware these might impact the local availability of project supplies. We have stocked project supplies. and are monitoring the situation.

## Guidance Delivery Chain Risk
Ocean Community Empowerment and Nature Grants Programme (OCEAN) Delivery Chain Risk Map Template - GUIDANCE
Delivery Chain Risk Mapping
Delivery Chain Risk Mapping (DCRM) is a useful tool for risk management in monitoring processes and improve understanding of how funding flows throughout a delivery chain, to ensure that programmes achieve their objectives. With this understanding we can: - Understand a delivery partner’s role in achieving the Outcome and opportunities for potential scale up. - Capture and manage risks that could affect the Outcome. - Ensure risks are being managed by those best placed to do so. - Strengthen our programme management capacity and delivery.
DCRM is a visual depiction in understanding, capturing, and managing the risks to the successful delivery of a programme, in relation to downstream delivery partners. It should, where possible, identify all partners (funding and non-funding e.g. legal/contributions in kind) involved in the delivery of the project. Delivery chain risk mapping captures details of: - The name of all downstream delivery partners and their functions. - Funding distributed to each delivery partner. - High level risks involved in programme delivery, mitigating measures and associated controls.
A good delivery chain risk map will: - Provide a clear understanding of all delivery partners involved in the delivery of a programme and the relationships between them. - Identify key delivery risks, mitigating measures and associated controls throughout the delivery chain. - Help ensure suitable risk management throughout the delivery chain.
As they are part of the Risk Framework, maps should be reviewed and updated periodically, with any material changes recorded as soon as possible.
OCEAN Grants Programme's Projects: Projects will need to complete the delivery chain risk map template. The delivery chain risk map captures risks specific to the delivery model and tiered funding structure. There may be some risks should be captured in both risk register and delivery chain risk map. For example, there may be delivery chain risks that could impact on the overall project outcome if they materialised, but not all delivery chain risks need to be duplicated in the project risk register. There should however be at least one overarching and high-level delivery chain risk that records the overall risk associated with your delivery model, whether that is direct implementation or through delivery partners.

## Guidance Issue Register
Ocean Community Empowerment and Nature Grants Programme (OCEAN) Issue Register Template - GUIDANCE
Issue | Date Added | Enter in the date that you added the identified the issue into this register using the format: DD/MM/YYYY. The date does not change, it remains as a historical record of when the issue was first identified.
| Issue Name | Give your identified issue a succinct single sentence title.
| Issue Description | Describe the issue succinctly in 1-3 sentences with a good, clear understanding of the three key elements of an issue: - the cause of the issue - the event or situation itself - the impact of the issue on the project
| Priority | Is your issue a Low, Medium or High priority? Please choose from the drop down menu in this column.
| Severity | What is the assessed impact of the issue on the project if no action is taken: Minor - Limited reduction in outcomes if this occurs Moderate - Higher but still limited loss in outcomes if this occurs Major - Outcomes reduced if this occurs but some important outcomes still likely Severe - Very significant reduction in outcomes when this occurs Please choose from the drop down menu in this column.
| Issue owner | Who is the owner of the issue? Who is responsible for monitoring and taking action on this identified issue? The person could be within your organisation or within your downstream implementing partner organisation. There can only be one owner per issue. Enter their full name, their job title and specify which organisation they are from.
Action | Status | Is the status of the issue: Open - the issue is being monitored, but no actions are being taken Investigating - the issue is under investigation to understand it, and develop the response Implementing - the response to issue is being implemented Escalated - the issue has been brought to the attention of more senior staff, partner or funder (Defra) Resolved - the issue has been resolved or is no longer considered an issue Please choose from the drop down menu in this column.
| Action | Describe your action to mitigate or resolve the issue, including escalation decisions, with a brief summary of any activities taken since the last update. Have any event(s) occurred that led to the issue increasing, decreasing or remaining steady in priority or severity? How has the wider context changed in the meantime? Have new mitigations been undertaken since the last update? If the issue is being closed, what led to it being resolved? Any entry should be dated, and all previous entries should be left in the cell for a historical record with the most recent entry at the top of the cell.

## Project Risk Register
Ocean Community Empowerment and Nature Grants Programme (OCEAN) Risk Register Template
Please read the guidance before completing your risk register.
Enter one risk per row. Do not leave blank rows between risks.
Application reference number:
Project title:
Lead organisation:
Project start date:
Project end date:
Risk contact:
Last update:
Risk Description | [5 empty] | Inherent Risk |  |  | Risk Mitigation |  |  | Residual Risk |  | Updates
| A short name for the risk | New/Emerging, Open, Closed | Briefly: the cause of the risk, the risk itself, and the impact of the risk | Identify risk against the 7 Risk Types | Name, job title and organisation | The likelihood of the risk materialising | The impact if the risk materialises | (autocalculated) |  | Any actions or controls to respond/mitigate the risk | The likelihood of the risk materialising | The impact if the risk materialises | (autocalculated) | See guidance
Date Added | Risk Name | Risk Status | Description of risk | Risk Type | Risk Owner | Probability | Impact | Risk Rating | Risk Response Type | Mitigating Action | Probability 2 | Residual Impact | Risk Rating4 | What's changed this reporting period?

## Delivery Chain Risk Map
Ocean Community Empowerment and Nature Grants Programme (OCEAN) Delivery Chain Risk Map Template
Please read the guidance before completing your delivery chain risk map.
| Tier 0 OCEAN Grants Programme |  |  | Flow of funding
| Tier 1 OCEAN Grants Administrator (NIRAS) |  |  | Lines of Reporting and Accountability
Tier 2 Lead Organisation
| Organisation Name: | Total funds in £GBP to the Lead Organisation | Identified risks at Tier 2 level | Controls and mitigations for identified risks
Tier 3 Project Partner(s)
(please specify if risk outlined is only relevant to a particular partner)
| Organisation Name: | Total funds in £GBP for each Partner Organisation | Identified risks at Tier 3 level | Controls and mitigations for identified risks
Tier 4 Project Partner(s)
Please specify if risk outlined is only relevant to a particular partner.
| Organisation Name: | Total funds in £GBP for each Tier 4 Partner Organisation, and name of Tier 3 organisation providing the funds | Identified risks at Tier 4 level | Controls and mitigations for identified risks

## Issue Register
Ocean Community Empowerment and Nature Grants Programme (OCEAN) Issue Register Template
Please read the guidance before completing your issues register.
Enter one issue per row. Do not leave blank rows between issues.
Please do not complete this worksheet when submitting your application.
Issues are relevant events (including materialised risks) that have occurred, but which were not planned and require management action after the project has started. As such this table is not needed during the planning phase, only once the project starts and the first issue is identified.
Issue | [5 empty] | Action
Date Added | Issue name | Issue description | Priority | Severity | Issue owner | Status | Action

## Dropdown lists (hidden)
Impact | Probability | Risk Response Type | Category
Insignificant | Rare | Threat - Avoid | Contextual
Minor | Unlikely | Threat - Reduce | Delivery
Moderate | Possible | Threat - Transfer | Safeguarding
Major | Likely | Threat - Share | Operational
Severe | Almost certain | Threat - Accept | Fiduciary
|  | Threat - Prepare contingent plans | Reputational
|  | Opportunity - Exploit | Other
Trend | Status | Opportunity - Enhance
Steady | New/Emerging | Opportunity - Transfer
Upwards | Open | Opportunity - Share
Downwards | Closed - the risk materialised | Opportunity - Accept
Closed - the risk didn't materialise
Priority |  | Issue Status
Low |  | Open
Medium |  | Investigating
High |  | Implementing
Escalated
Resolved